## Sheet1
Bug ID | Bug Name | Description | Priority | Severity | Steps to Reproduce | Expected Result | Actual Result | Status | Assigned To | Remark
BUG-001 | Leave Encasement Calculation Error | The leave encasement calculation does not include carry-forwarded leaves, leading to incorrect payout. | High | Major | 1. Navigate to Leave Encasement. 2. Select employee with carry-forwarded leaves. 3. Calculate encasement. | Encasement amount should include all eligible leaves including carry-forwarded ones. | Encasement excludes carry-forwarded leaves and shows lesser payout. | Open
BUG-002 | Leave Request Submission Fails | Employees are unable to submit leave requests — form throws server error on submission. | High | Critical | 1. Login as employee. 2. Go to Leave Management → Apply Leave. 3. Fill form and submit. | Leave request should be submitted successfully and show under pending approvals. | Server error (500 Internal Server Error) shown, request not submitted. | Open
BUG-003 | Incorrect Pay Grade Display | Pay grade details show incorrect salary range for some grades after editing. | Medium | Major | 1. Login as admin. 2. Go to Pay Grade Management. 3. Edit an existing pay grade. 4. Save changes and view. | Edited pay grade should display updated salary range correctly. | Pay grade still shows old salary range despite showing 'Saved successfully' message. | Open
BUG-004 | Leave Balance Not Updated After Approval | Leave balance does not decrease after approved leave, showing wrong available leave count. | High | Major | 1. Approve a pending leave request as admin. 2. Check employee's leave balance. | Leave balance should decrease based on approved leave days. | Leave balance remains unchanged even after approval. | Open
BUG-005 | Pay Grade Deletion Crashes System | Attempting to delete a pay grade record crashes the system with a fatal error. | Critical | Critical | 1. Login as admin. 2. Navigate to Pay Grade Management. 3. Select a pay grade and click delete. | Pay grade should be deleted successfully without crashing the system. | System crashes with 'Fatal error: Uncaught Exception' message. | Open